Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date: 03/10/2026 | Team ID: 6ab8f707c23107aaaa73276f |
| --- | --- |
| Project Name: Auto Ticket Classification using Flow Designer | Maximum Marks: 5 Marks |

Product Backlog, Sprint Schedule, and Estimation

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Table & Schema Configuration | USN-1 | Create custom Incident WorkFlow table with required fields (Number, Caller, Short Description, Category, Subcategory). | 3 | High | Amar |
| Sprint-1 | Data Model Setup | USN-2 | Configure dependent choice lists for Category (Network, Hardware, Access, Performance) and dependent Subcategories. | 3 | High | Yuktesh |
| Sprint-1 | Trigger Setup | USN-3 | Configure Flow Designer trigger on Incident table record creation with guardrail condition [Category IS EMPTY]. | 2 | High | Amar |
| Sprint-1 | Keyword Evaluation Logic | USN-4 | Build conditional logic branches in Flow Designer to evaluate keywords ('Wi-Fi', 'Projector', 'Password', 'Slow PC'). | 5 | High | Yuktesh |
| Sprint-1 | Automated Field Update | USN-5 | Implement automated record update action to populate Category and dependent Subcategory dynamically. | 3 | High | Team |
| Sprint-2 | Automated Caller Notification | USN-6 | Create outbound email notification action pulling Caller profile dynamically via sys_user reference pill. | 3 | High | Yuktesh |
| Sprint-2 | Exception & Fallback Handling | USN-7 | Implement fallback conditional logic: route unmatched tickets to Category 'Other' and assign to Tier 1 Triage queue. | 2 | Medium | Amar |
| Sprint-2 | End-to-End Test Execution | USN-8 | Execute test scenarios for all keywords (Wi-Fi, Projector, Password, Slow PC) and verify sub-second execution (~180 ms). | 5 | High | Team |
| Sprint-2 | Update Set Packaging | USN-9 | Capture table schema, choices, and Flow Designer configurations into a global ServiceNow Update Set (XML). | 3 | Medium | Amar |
| Sprint-2 | Documentation & Metrics Review | USN-10 | Document system architecture, accuracy metrics (94.2%), and weekly reclaimed triage hours (15 hrs). | 3 | Medium | Team |

Project Tracker, Velocity & Burndown Chart

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 16 | 6 Days | 14 Sep 2026 | 19 Sep 2026 | 16 | 19 Sep 2026 |
| Sprint-2 | 16 | 6 Days | 21 Sep 2026 | 26 Sep 2026 | 16 | 26 Sep 2026 |

Velocity Calculation (Agile Scrum Metrics):

Total Story Points Completed = Sprint 1 (16) + Sprint 2 (16) = 32 Story Points Number of Sprints = 2 Sprints (Duration: 6 working days per sprint) • Velocity (Story Points per Sprint) = Total Story Points Completed / Number of Sprints Velocity = 32 / 2 = 16 Story Points per Sprint • Average Velocity (AV per day) = Velocity / Sprint Duration AV = 16 / 6 = 2.67 Story Points per Day

Sprint Burndown Chart Tracking (Work Remaining vs. Day)

| Day | Sprint-1 Ideal Points | Sprint-1 Actual Points | Sprint-2 Ideal Points | Sprint-2 Actual Points |
| --- | --- | --- | --- | --- |
| Day 0 (Sprint Start) | 16.0 | 16 | 16.0 | 16 |
| Day 1 | 13.3 | 13 (USN-1 done) | 13.3 | 13 (USN-6 done) |
| Day 2 | 10.7 | 10 (USN-2 done) | 10.7 | 11 (USN-7 in progress) |
| Day 3 | 8.0 | 8 (USN-3 done) | 8.0 | 8 (USN-7 done) |
| Day 4 | 5.3 | 5 (USN-4 in progress) | 5.3 | 5 (USN-8 in progress) |
| Day 5 | 2.7 | 3 (USN-4 done) | 2.7 | 3 (USN-8 done, USN-9 done) |
| Day 6 (Sprint End) | 0.0 | 0 (USN-5 done) | 0.0 | 0 (USN-10 done) |